## Planning
Description	Estimate Time (In hours)	Delivery Date (Initial)	Start Date	Delivery Date (End)	Status
MANAGEMENT OF REGISTER				-			Legend	Color
							Do it
FR01. Register of the user	2			-			In progress
							To do
MANAGEMENT OF LOG IN				-

FR02. Log in	2			-
FR03. Change Password	2			-

MANAGEMENT OF LOG OUT				-

FR04. Log out	2			-

MANAGEMENT OF LANGUAGE				-

FR05. Language of the web site	2			-

MANAGEMENT OF CATEGORIAS				-

FR06. Add category	4			-
FR07. Modify category	2			-
FR08. Delete category	2			-

MANAGEMENT OF ARTICLES				-

FR09. Add articles	4			-
FR10. Modify articles	4			-
FR11. Delete articles	2			-

MANAGEMENT OF CARDS				-

FR12. Add cards	8			-
FR13. Modify cards	2			-
FR14. Delete cards	2			-

MANAGEMENT OF SEARCH				-

FR15. Search for name	8			-
FR16. Search for category	8			-
FR17. Filters	8			-

MANAGEMENT OF VALUATIONS				-

FR18. Value cards	2			-
FR19. Value articles	2			-
FR20. Value comments	2			-

MANAGEMENT OF COMMENTS				-

FR21. Add a comment	2			-
FR22. Delete a comment	2			-
FR23. Modify a comment	2			-
FR24. Report a comment	2			-

MANAGEMENT OF PRIVATE MESSAGES				-

FR25. Private message	8			-
FR26. Inbox	8			-

MANAGEMENT OF RANKING				-

FR27. Ranking	8			-